## AAD
SKCT - CSE IT AIDS - Advanced Application Development Planner
Date | Day |  | Topics | ` | Description | `Q1
13.03.2024 | 1 | Frontend | Project Setup | Project Setup, Analysis | Setting up React Project Environment using Vite Template, Folder Structure, and GitHub. Design and Component Analysis, along with the Frontend Module Report.
14.03.2024 | 2 |  | Public Routes & Public Components & Layouts | Public Components Preloader Layouts with CSS | Designing the Navbar and Footer, as well as components for job listings (Landing page design), and Login & Register. Implement the preloader concept using React's <Suspense>. Design the side bar and top bar components for the admin and user panels using CSS.
15.03.2024 | 3 |  | User | Profile Settings Components | Designing components for editing phone number, email, and password, along with other components.
16.03.2024 | 4 |  | Admin | Admin User Components | Designing components for User Management. Create User CRUD (Create, Read, Update, Delete) Components.
18.03.2024 | 5 |  | Admin | Admin Settings | Designing components for Admin Profile & Password and Site Settings.
19.03.2024 | 6 |  | Review 1
20.03.2024 | 7 | Backend | Project Setup | Project Setup Schema | Planning and setting up required modules and an online PostgreSQL database (SQL DB). Planning the database schema based on requirements.
21.03.2024 | 8 |  | Models & Roles & DTO | Models DTO | Implementing User & Admin, and workspace. Implementing Request & Response DTOs for all models.
22.03.2024 | 9 |  | Security Config | Spring Security | Setting up HTTP filters, session policies, CORS, and CSRF configurations.
23.03.2024 | 10 |  | Security Config | JWT | Configuring JWT, Implementing Roles (User & Admin), Auth DTO
25.03.2024 | 11 |  | Services | Logics | Implementing services for all models, including business logic, data validation, and interaction with the database.
26.03.2024 | 12 |  | Controllers with Security & SwaggerUI | Controllers and SwaggerUI | Implementing CRUD controllers and authentication controllers with endpoint security based on role-based access control. Setting up Swagger Tags for all Endpoints
27.03.2024 | 13 |  | Review 2
28.03.2024 | 14 | Integration | Protected Routes | Axios API Services & Conditional Auth Routing | Writing API services with Axios in React. Implementing private routes using React Router or another routing library.
01.04.2024 | 15 |  | User Integration | Auth & User Components Integration with Protected Routes | Integrating Login & Register, managing User Sessions using Session Tokens Integrating Profile
02.04.2024 | 16 |  | Admin Integration and Payment Gateway Integration | Admin Auth & Admin Components integration with Protected Routes | Integrating Admin Authentication, managing Admin Sessions using Session Tokens. Integrating User Components. Integrating Admin Profile, Integrating Payment Gateway Like Razor pay and CCAvenue in Admin
03.04.2024 | 17 | Deployment | Aws Config Docker | Security Groups EC2 Docker Install | Creating a network security group and setting inbound and outbound rules. Setting up an EC2 instance with either an AMI or Ubuntu micro instance. Installing and configuring Docker inside the EC2 instance.
04.04.2024 | 18 |  | Spring Deployment React Deployment | Neon Console & Postgres Migration DOCKERFILE for Backend Build & Run DOCKERFILE for Frontend Build & Run | Adding PostgreSQL drivers in the POM file and updating local database properties to Neon credentials. Setting up a Dockerfile containing Java version and Spring Boot version configurations for the backend. Building the Docker image inside the EC2 instance using the Dockerfile and starting the backend container with the Dockerfile. Setting up a Dockerfile containing Node.js version and Nginx version configurations for the frontend. Building the Docker image inside the EC2 instance using the Dockerfile and starting the frontend container with the Dockerfile.
05.04.2024 | 19 |  | Final Review (Review 3)